## Taul1
Failure Mode | Effects | Causes | Severity | Occurrence | Detection | RPN | Mitigation Actions
Compatibility Issues | Features break, integrations stop working | Changes to system | 8 | 5 | 5 | 200 | Maintain backward compatibility, regression tests
User resistance to change | Low adoption, decreased productivity | Unfamiliar UI | 6 | 7 | 4 | 168 | Gather feedback early, provide training
Security vulnerabilities | Data breaches | Poor encryption, insufficient authentication | 10 | 3 | 6 | 180 | Enforce encryption, perform security audits
Poor performance | Unresponsive system, user dissatisfaction, helpdesk queues |  | 6 | 4 | 6 | 144 | Performance monitoring
Missing features | User dissatisfaction |  | 3 | 10 | 7 | 210 | Catalogue features for migration, extend legacy system lifespan
Excessive bugs | System works poorly, user dissatisfaction, helpdesk queues | Poor unit test coverage, insufficient testing | 7 | 6 | 5 | 210 | Test driven development, CI/CD pipelines, testing resources
High cost | Insufficient budget, delays | Poor estimates, scope creep | 7 | 5 | 7 | 245 | Prioritize minimum viable product, perform cost-benefit analysis
0
0
0
0
0
0
0
0
0
0